## Sheet1
PROJECT X - Automated Attendance System
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Estimated Hours | Assignee | Start Date | End Date | Status | Actual Hours Spent | Notes
1 | Project Injection | 1.1 | Requirements Gathering | Requirements Document | 4 | Ella Mae Ventura | 02/27/2025 | 02/27/2025 | Done | 3
|  | 1.2 | Project Viability Assessment | Feastibility Report | 6 | Nikki Matinagnos | 02/28/2025 | 2025-01-03 | Done | 4
|  | 1.3 | Stakeholder Assessment | Stakeholder Report | 5 | Ivan Kyle Lingo | 2025-01-03 | 2025-02-03 | Done | 5
|  | 1.4 | Risk Analysis & Mitigation | Risk Analyis Report | 6 | Ella Mae Ventura | 2025-01-03 | 2025-02-03 | Done | 6
|  | 1.5 | Project Planning & Timeline | Task Allocation & Dependencies | 5 | Nikki Matinagnos | 2025-01-03 | 2025-02-03 | Done | 5
|  | 1.6 | Approval & Initiation Meeting | Project Timeline & Milestones | 6 | Ella Mae Ventura | 2025-01-03 | 2025-02-03 | Done | 4
2 | System Design | 2.1 | Database Schema Design | ER Diagram, Schema Scripts | 5 | Ivan Kyle Lingo | 2025-02-03 | 2025-01-08 | Done | 5
|  | 2.2 | UI/UX Wireframes & Prototypes | Wireframes, UI Mockups | 7 | Nikki Matinagnos | 2025-02-03 | 2025-01-09 | Done | 4
|  | 2.3 | System Structure & Technical Blueprint | Architecture Diagram | 8 | Nikki Matinagnos | 2025-03-03 | 2025-01-10 | Done | 5
|  | 2.4 | Endpoint Design & Integration Guide | Authentication & Authorization Guidelines | 10 | Ella Mae Ventura | 2025-03-03 | 2025-01-11 | Done | 5
|  | 2.5 | Technology Stack Finalization | Tech Stack Specification | 10 | Ivan Kyle Lingo | 2025-04-03 | 2025-01-12 | Done | 6
|  | 2.6 | Security & Compliance Planning | Security Compliance Document | 5 | Nikki Matinagnos | 2025-04-03 | 2025-01-13 | Done | 5
3 | Development | 3.1 | Frontend - Login & Dashboard | UI Components | 5 | Ella Mae Ventura | 2025-05-03 | 2025-06-03 | Done | 6
|  | 3.2 | Frontend - Attendance Interface | Attendance UI | 5 | Ella Mae Ventura | 2025-05-03 | 2025-06-03 | Done | 6
|  | 3.3 | Backend - Authentication | User Authentication API | 7 | Ivan Kyle Lingo | 2025-06-03 | 2025-07-03 | Done | 6
|  | 3.4 | Backend - Attendance Logic | Attendance Tracking API | 10 | Ivan Kyle Lingo | 2025-10-03 | 2025-11-03 | Done | 5
|  | 3.5 | Database Integration | Functional Database | 10 | Ivan Kyle Lingo | 2025-11-03 | 2025-12-03 | Done | 6
|  | 3.6 | RFID/Biometric Integration | Functional Attendance System | 7 | Ella Mae Ventura | 2025-12-03 | 03/13/2025 | Done | 7
|  | 3.7 | Role-Based Access Control | Authentication System | 7 | Ivan Kyle Lingo | 2025-12-03 | 03/13/2025 | Done | 6
|  | 3.8 | Notification System (Email/SMS) | Notification Module | 7 | Jhomarie Avenido | 03/13/2025 | 03/14/2025 | Done | 5
4 | Testing | 4.1 | Unit Testing | Test Cases, Bug Reports | 6 | Nikki Matinagnos | 03/15/2025 | 03/16/2025 | Done | 5
|  | 4.2 | Integration Testing | Integration Test Report | 6 | Ella Mae Ventura | 03/16/2025 | 03/17/2025 | Done | 6
|  | 4.3 | User Acceptance Testing (UAT) | UAT Feedback Report | 7 | Ella Mae Ventura | 03/16/2025 | 03/17/2025 | Done | 5
5 | Deployment | 5.1 | Deployment to Staging | Staging Environment Setup | 8 | Ivan Kyle Lingo | 03/18/2025 | 03/19/2025 | Done | 5
|  | 5.2 | Production Deployment | Live System | 8 | Ivan Kyle Lingo | 03/20/2025 | 03/21/2025 | Done | 6
|  | 5.3 | Training & Documentation | User Guide, Training Sessions | 8 | Ella Mae Ventura | 03/25/2025 | 03/26/2025 | Done | 5
6 | Maintenance | 6.1 | Bug Fixes & Minor Updates | Patch Releases | 9 | Ivan Kyle Lingo | 03/28/2025 | 03/29/2025 | Done | 5
|  | 6.2 | Security & Monitoring | Security Patches, Logs | 10 | Ivan Kyle Lingo | 2025-03-04 | 2025-04-04 | Done | 5